CAPSTONE PROJECT REPORT

Report 2 – Project Management Plan

CourtConnect_Web application for Finding Badminton Courts and Playmates

– Hanoi, August 2024 –

# Table of Contents

I. Record of Changes	3

II. Project Management Plan	4

1. Overview	4

1.1 Scope & Estimation	4

1.2 Project Objectives	4

1.3 Project Risks	4

2. Management Approach	5

2.1 Project Process	5

2.2 Quality Management	5

2.3 Training Plan	5

3. Project Deliverables	5

4. Responsibility Assignments	5

5. Project Communications	6

6. Configuration Management	6

6.1 Document Management	6

6.2 Source Code Management	6

6.3 Tools & Infrastructures	6

# I. Record of Changes

| Date | A* M, D | In charge | Change Description |
| --- | --- | --- | --- |
| 20-05-2024 | A | Nguyen Hong Quan | 6. Configuration Management |
| 20-05-2024 | A | Nguyen Toan Thang | 1.1 Scope & Estimation |
| 20-05-2024 | A | Nguyen Duy Anh | 3. Project Deliverables |
| 21-05-2024 | M | Nguyen Duy Anh | 3. Project Deliverables |
| 21-05-2024 | A | Nguyen Duy Anh | 4. Responsibility Assignments 5. Project Communications |
| 21-05-2024 | A,M | Nguyen Toan Thang | 1.1 Scope & Estimation 1.2 Project Objectives 1.3 Project Risks |
| 21-05-2024 | A | Le Duc Manh | 2. Management Approach |
| 25-05-2024 | M | Nguyen Toan Thang | 1.1 Scope & Estimation |
| 29-05-2024 | M | Nguyen Hong Quan | 1.2 Project Objectives |
| 25-06-2024 | M | Nguyen Hong Quan | 1.3 Project Risks |
| 25-06-2024 | M | Nguyen Hong Quan | 2. Management Approach |
| 25-06-2024 | M | Nguyen Hong Quan | 3. Project Deliverables |
| 25-06-2024 | M | Nguyen Hong Quan | 1.2 Project Objectives |
| 25-06-2024 | M | Nguyen Hong Quan | 4. Responsibility Assignments |
| 25-06-2024 | M | Nguyen Hong Quan | 5. Project Communications |
| 25-06-2024 | M | Nguyen Hong Quan | 1.2 Project Objectives |

*A - Added M - Modified D - Deleted

# II. Project Management Plan

## 1. Overview

### 1.1 Scope & Estimation

| # | WBS Item | Complexity | Est. Effort (man-days) |
| --- | --- | --- | --- |
| 1 | Authentication |  | 20 |
| 1.1 | Register | Medium | 4 |
| 1.2 | Login | Hard | 10 |
| 1.3 | Logout | Simple | 2 |
| 1.4 | Forgot Password | Simple | 2 |
| 1.5 | Change Password | Simple | 2 |
| 2 | Admin Feature |  | 60 |
| 2.1 | Create attribute branch | Hard | 5 |
| 2.2 | Update attribute branch | Simple | 5 |
| 2.3 | View attribute branch | Simple | 5 |
| 2.4 | Delete attribute branch | Simple | 5 |
| 2.5 | Create attribute court | Hard | 5 |
| 2.6 | Update attribute court | Simple | 5 |
| 2.7 | View attribute court | Simple | 5 |
| 2.8 | Delete attribute court | Simple | 5 |
| 2.9 | View list account | Simple | 5 |
| 2.10 | View detail account | Simple | 5 |
| 2.11 | Ban/unban account | Simple | 5 |
| 2.12 | Accept branch | Simple | 5 |
| 3 | Manage branch |  | 50 |
| 3.1 | Register branch | Hard | 10 |
| 3.2 | Update branch | Medium | 10 |
| 3.3 | Delete branch | Simple | 10 |
| 3.4 | View list branch | Medium | 10 |
| 3.5 | View detail branch | Simple | 10 |
| 4 | Manage court |  | 30 |
| 4.1 | Create court | Medium | 6 |
| 4.2 | Update court | Simple | 6 |
| 4.3 | Delete court | Simple | 6 |
| 4.4 | View list court | Simple | 6 |
| 4.5 | View detail court | Simple | 6 |
| 5 | Booking court |  | 75 |
| 5.1 | View available courts | Simple | 10 |
| 5.2 | Filter court | Medium | 15 |
| 5.3 | View detail court | Simple | 15 |
| 5.4 | Book court | Simple | 10 |
| 5.5 | View match calendar | Medium | 10 |
| 5.6 | Change booked match | Simple | 15 |
| 6 | Finding matching |  | 80 |
| 6.1 | Create post find other players | Medium | 15 |
| 6.2 | View registration list | Medium | 15 |
| 6.3 | View waiting list | Medium | 15 |
| 6.4 | Register to booked court | Medium | 15 |
| 6.5 | Invite other | Medium | 15 |
| 6.6 | Response to request | Medium | 15 |
| 7 | View matches participated |  | 10 |
| 7.1 | View history booking | Simple | 5 |
| 7.2 | View history send registered matched | Simple | 2 |
| 7.3 | View matches participated | Medium | 3 |
| 8 | Manage blogs |  | 25 |
| 8.1 | Delete blog | Simple | 5 |
| 8.2 | View list blog | Simple | 5 |
| 8.3 | View detail blog | Simple | 5 |
| 8.4 | Report blog | Medium | 5 |
| 8.5 | Comment blog | Medium | 5 |
| 9 | Notification |  | 10 |
| 10 | Real-time |  | 10 |
| 11 | Statistics |  | 15 |
| 11.1 | Account statistics | Hard | 5 |
| 11.2 | Revenue statistics | Hard | 5 |
| 11.3 | Number of orders statistics | Hard | 5 |
| Total Estimated Effort (man-days) Assign time(man-days): 15 week * 5 * 5 days/week = |  |  | 385 375 |

### 1.2 Project Objectives

| # | Metric | Unit | Committed | Actual | Notes / Refs |
| --- | --- | --- | --- | --- | --- |
| 1 | Effort Usage | Person-day | 375 | On Going |  |
| 2 | Defect Rate | No. Def/MM | Dev: 10.0 | On Going |  |
| 3 | Review Efficiency | % | Dev: 20 | On Going | Static bug/total bugs |
| 4 | Leakage Rate | No. Def/MM | Dev: 0.2 | On Going |  |
| 5 | Timeliness | % | 95 | On Going |  |
| 6 | Requirement Completeness | % | 95 | On Going |  |

### 1.3 Project Risks

| # | Risk Description | Impact | Possibility | Response Plans |
| --- | --- | --- | --- | --- |
| 1 | Team member does not finish task on time | High | High | The other members should join forces to complete the unfinished task |
| 2 | Conflict in coding | High | High | Project manager revert to the nearest version and sync with new code |
| 3 | Members misunderstands requirements | Medium | Medium | Make sure members carefully read the requirements contained in the document and discuss sharing progress in meetings and reports |
| 4 | Requirement changes | High | Medium | All members should carefully discuss and confer with instructors to define scope and requirements |

## 2. Management Approach

### 2.1 Project Process

For the implementation of our Badminton arena management system, we will apply the Iterative Development process model. This model is chosen for its flexibility in accommodating changes, continuous improvement, and focus on refining the product through repeated cycles.

- Planning Phase: Define the scope and objectives of the project, establish requirements, and plan the initial iteration.

- Design Phase: Create a high-level design for the system, which will be refined and expanded in each iteration.

- Implementation Phase: Develop the system in small, manageable segments, each adding incremental functionality.

- Testing Phase: Test the segments developed in each iteration to identify and fix defects early.

- Evaluation Phase: Review the outcomes of each iteration with stakeholders to gather feedback and make necessary adjustments.

- Repeat Cycles: Continue iterating through the design, implementation, testing, and evaluation phases until the final product meets the project requirements.

### 2.2 Quality Management

- Defect Prevention:

  - Use coding standards and best practices.

  - Conduct regular code reviews to catch issues early.

- Reviewing:

  - Peer Reviews: Conduct regular code and design reviews by team members to catch defects early and ensure adherence to coding standards and best practices.

- Unit Testing:

  - Develop and run automated tests for individual components to ensure they function correctly in isolation.

  - Focus on testing the smallest units of code, such as functions or methods, to catch defects early in the development cycle.

- Integration Testing:

  - Test the integration points between different modules to detect and fix interface defects.

  - Ensure that modules work together as expected and data is correctly passed between them.

- System Testing:

  - Conduct end-to-end testing of the complete system to ensure it meets all specified requirements.

  - Simulate real-world usage scenarios to validate the system's performance, security, and usability.

### 2.3 Training Plan

| Training Area | Participants | When, Duration | Waiver Criteria |
| --- | --- | --- | --- |
| Git, GitHub | All team member | First week, 1 week. | Mandatory |
| Amazon Web Service | Pham Hai Minh, Nguyen Duy Anh, Le Duc Manh | Eighth week, 2 week | Team members who do not participate in back-end coding or deployment. |
| MySQL | Le Duc Manh | Second week, 1 week | Team members who already process required knowledge about MySQL. |
| Testing | Pham Hai Minh | Tenth week, 1 week | Team members who do not participate in the testing process |

## 3. Project Deliverables

| # | Deliverable | Due Date | Notes |
| --- | --- | --- | --- |
| 1 | Prepare Project Introduction Document | 09/05/2024 | Overview of the project, goals, and scope |
| 2 | Project Planning & Tracking | 09/05/2024 | Project initialization and functional deployment |
| 3 | Prepare SRS Document (Overview Part) | 26/05/2024 | User requirements and use cases |
| 4 | Prepare SRS Document (User Requirements) | 26/05/2024 | Detailed software design, system architecture |
| 5 | Software Design Document | 09/06/2024 | Detailed software design, system architecture |
| 6 | Test Documentation | 20/07/2024 | Testing plan and strategy |
| 7 | Unit Test | 06/08/2024 | Unit testing, ensuring individual modules function correctly |
| 8 | Integration Test | 06/08/2024 | Integration testing, ensuring modules work together correctly |
| 9 | System Test | 06/08/2024 | Integration testing, ensuring modules work together correctly |
| 10 | Software User Guides | 10/08/2024 | End-user software guides |
| 11 | Report7_Final Project Report | 10/08/2024 | Final project summary report |

## 4. Responsibility Assignments

D~Do; R~Review; S~Support; I~Informed; <blank>- Omitted

| Responsibility | Anhndhe161107 | Quannhhe161642 | Thangnthe163199 | Manhldhe160520 | Minhphhe153421 |
| --- | --- | --- | --- | --- | --- |
| Project Planning & Tracking | D | D | D | D | D |
| Prepare Project Introduction Document | D | D | D | D | D |
| Prepare SRS Document (Overview Part) | S | D | S | S | R |
| Prepare SRS Document (User Requirements) | S | D | S | S | R |
| Project Weekly Report_G23 | S | D | S | S | R |
| Software Design Document | D | D | D | D | D |
| Test Documentation | S | S | S | S | D |
| Unit Test | S | S | S | S | D |
| Integration Test | S | D | S | S | D |
| System Test | S | D | S | D | D |

## 5. Project Communications

| Communication Item | Who/ Target | Purpose | When, Frequency | Type, Tool, Method(s) |
| --- | --- | --- | --- | --- |
| Kick-off Meeting | Project Team | To officially start the project and align objectives | Start of the project | Live meeting via Google Meet |
| Weekly Status Report | Project Team | To update on project progress, issues, and next steps | Weekly | Email, Trello |
| Progress Meeting | Project Team | To discuss progress, address any roadblocks | Weekly | Video conference, In-person meeting |
| Announcement of Match Schedule | Players, Spectators | Announce the time and location of the competition | Before each tournament | Post information on the website, send an email |
| Risk Management Report | Project Manager, Risk Team | To identify and mitigate potential risks | Monthly | Email, Risk Management Software |
| Milestone Review | Project Team, Stakeholders | To review completed milestones and plan the next steps | At each project milestone | Email |
| Project Final Report | Management Board, Sponsors | Summary of project results and lessons learned | After finishing the project | Detailed reports and notes |
| Satisfaction Survey | Players, Spectators | Evaluate satisfaction level, and collect feedback After each tournament and event | After each event | Send survey link via email |
| News & Updates | Community, Players | Update news about activities and upcoming tournaments | Weekly or as needed | Post articles, send emails |

## 6. Configuration Management

### 6.1 Document Management

All documents will be stored on Google Drive and shared with supervisors. We use Google Docs and

Google Sheets as our primary tools for sharing documents and Weekly Reports. It allows us to

observe what changes were made in the document and who was responsible for the modification, as well as compare versions of the document at the same time.

### 6.2 Source Code Management

Source code is managed by GitHub. GitHub makes it easier to store, upload, and download code

every time you need to. Control changes in code quickly and accurately. It easily manages, distributes

work and complete programming projects of better quality. The team leader is the person who will

review and merge the team members' code. New team members and supervisors can access the

repository on GitHub.

### 6.3 Tools & Infrastructures

| Category | Tools / Infrastructure |
| --- | --- |
| Technology | React (FrontEnd), Express (BackEnd) |
| Database | MySQL |
| IDEs/Editors | Visual Studio Code |
| Diagramming | DrawIO |
| Documentation | Google Docs/Sheets/Slides |
| Version Control | GitHub (Source Codes), Google Drive (Documents) |
| Deployment server | Amazon Web Service |
| Project management | Trello |